## Test Plan
Sr. No. | Test Plan Point | Answer
1 | Test Plan Identifier | E-Learn-TestPlan-V1.0
2 | References | SRS Document v1.0, Design Document v1.0, IEEE 829 Test Plan Standard
3 | Introduction | The Online Learning Platform aims to provide students and instructors with course creation, enrollment, and assessment modules through a secure web-based interface.
4 | Features to be Tested | User Registration/Login, Course Management, Video Lectures, Assignments, Discussion Forum, Payment Gateway, and Performance Analytics.
5 | Approach | Testing will follow a hybrid approach using both Manual and Automation Testing. Functional, Integration, System, and Acceptance tests will be conducted using Black Box techniques.
6 | Environmental Needs | Windows 10/11 OS, Chrome Browser, Node.js backend, React frontend, MongoDB database, Postman for API testing, Selenium for automation.
7 | Staffing & Training Needs | Testing Team: 1 Test Manager, 2 Test Engineers. Training on test management tools (Jira) and automation frameworks (Selenium, Jest).
8 | Responsibilities | Test Manager: Planning & Reporting. Test Engineers: Test case execution, Defect logging. Developers: Fix defects and perform unit testing.
9 | Schedule | Test Planning: 10 Nov – 12 Nov; Test Design: 13 Nov – 16 Nov; Test Execution: 17 Nov – 22 Nov; Reporting: 23 Nov – 25 Nov 2025.
10 | Approval | Project Manager: [Name], QA Lead: [Name], Date: 25-Nov-2025

## Test Cases
Test Case ID | Test Scenario/Step | Test Data | Expected Result | Actual Result | Pass/Fail
TC001 | User Registration | Valid Email, Password | Account should be created successfully
TC002 | User Login | Registered Email and Password | User should be logged in and redirected to dashboard
TC003 | Enroll in Course | Valid Course ID, Logged-in User | Enrollment confirmation message should appear
TC004 | Submit Assignment | Uploaded PDF File | Assignment should be uploaded successfully
TC005 | Watch Lecture Video | Click Play on Course Video | Video should play without buffering
TC006 | Attempt Quiz | Valid Answers Submitted | Score and result summary should display correctly
TC007 | Payment Gateway | Valid Card Details | Payment should be processed and receipt generated
TC008 | Discussion Forum | Post a Comment | Comment should appear instantly in the forum thread
TC009 | Performance Analytics | Student’s course data | Progress graph should display accurately
TC010 | Logout | Click Logout Button | User should be safely logged out of the system